## RACI Matrix Template
RACI Matriz
Task / Stakeholders | Stakeholder 1: Jonathan | Stakeholder 2: Catalina | Stakeholder 3: Yeira | Stakeholder 4: Rodrigo | Stakeholder 5: Oscar | RACI
Investigación preliminar del proyecto | I | A | I | C | R | R - Responsible The people who take action to get the task done. They are responsible for the work or making the decision. You can have more than one person responsible for a task, but to make the decision-making process effective, try having one person responsible for a single task. | A - Accountable The person who owns the task or deliverable. They might not get the work done themselves, but they are responsible for making sure it is finalized. To avoid confusion and the diffusion of responsibility, it’s better to have one accountable person per project task.
Definición del problema, objetivos y metas del proyecto | A | R | C | I | I
Selección de metodología de trabajo | I | A | I | C | R
Definición roles de trabajo | I | A | I | R | C | C - Consulted The person, role, or group who will help complete the task. They will have two-way communication with the people responsible for the task by providing input and feedback over the task completion. | I - Informed The people, roles, or groups that need to be up to date on the task’s progress. They will not have two-way communication, but it’s essential to keep them informed since they will be affected by the final outcome of the task/project.
Definición requerimientos de comunicación para el proyecto | R | A | C | I | I
Organización y planificación de actividades | A | C | R | I | I
Recoleción información procesos actuales | I | A | I | C | R
Clasificación de partes/procesos | I | A | I | R | C
Identificación proceso de fabricación actual | C | A | R | I | I
Identificación métricas actuales | A | R | C | I | I
Generación de alternativas | I | A | I | C | R
Evaluación técnica | A | R | C | I | I
Estimación de costos preliminares | C | A | R | I | I
Evaluación de impacto | I | A | I | R | C
Análisis multicriterio | C | R | A | I | I
Selección de alternativa | R | C | A | I | I
Revisión tareas y entregables | I | A | I | C | R
Especificación proceso de fabricación solución seleccionada | A | R | C | I | I
Identificación y planificación de bienes y servicios | A | C | R | I | I
Análisis de riesgos e implementación de medidas | I | A | I | R | C
Identificación de tecnologías industria 4.0 involucradas | I | A | I | C | R
Diseño infraestructura de automatización a nivel de Hardware | R | C | A | I | I
Estimación detallada de costos del proyecto | C | A | R | I | I
Evaluación de rentabilidad del proyecto | I | A | I | R | C
Elaboración propuesta comercial | I | A | I | C | R
Integración con entorno digital | R | A | C | I | I
Estructuramiento modelo ciberfísico con industria 4.0 | I | A | I | C | R
Implementación de lógica de control | R | A | C | I | I
Desarrollo sistema SCADA con validación de interfaz HMI | C | R | A | I | I
Desarrollo del modelo 3D de celda en Siemens NX | I | A | I | R | C
Modelamiento celda robotizada en RobotStudio | C | A | R | I | I
Documentación administración del proyecto | A | I | C | I | R
Documentación coordinación del proyecto | I | C | A | I | R
Registro experiencia de aprendizaje | I | I | C | R | A
Registro líneas de trabajo futuras | C | A | I | R | I
Reporte audivisual final | C | I | I | A | R
Actualización completa sitio en línea | R | I | A | I | C
Carga completa entregables | I | C | I | A | R
Revisión final proyecto | A | I | C | I | R